## Requirements
Name |  | Group 7
Client Name |  | MotorPH
REQUIREMENTS IDENTIFICATION
# | GUIDE QUESTIONS | ANSWER (Write your answer to the guide question based on your current understanding) | [8 empty] | ITEMS FOR CLARIFICATION (Identify items you need to clarify with your mentor)
| Member Name | FINALIZED | Jesus Elijah | Eugenio | Andre Al Fayed | Jovelyn | Shaira | Mitch | Leandra | Christian
1 | What problem is the client trying to resolve or what business need are they trying to fulfill? | The client, MotorPH, is seeking to address gaps and difficulties in their current payroll operations. Their primary business need is to find a more effective and efficient payroll management system with enhanced functionality, timeliness, and accuracy. This initiative is part of a broader goal to improve operational procedures across all areas of their firm. Specifically, they aim to automate and optimize internal processes related to employee management and payroll computations. The desired system should handle tasks such as presenting employee information, calculating hours worked, gross and net compensation, and deductions in an efficient manner. | In their present payroll operations, the customer is addressing gaps and difficulties. The objective is to find a payroll management system that is more effective and efficient, with enhanced functionality, timeliness, and accuracy. They want to improve operational procedures in every area of their firm, and this is a step toward that aim. | Employee Management and Payroll Automation | The client wants to automate and optimize internal procedures, particularly those that deal with payroll computations and employee data management. The objective is to create a system that can handle functions like presenting employee information, calculating hours worked, gross and net compensation, and deductions in an effective manner. | MotorPH is planning to open physical stores. In the next 18 months, the company is planning to open branches in different parts of the Philippines. | They are looking for a solution that can make their operations smooth, reduce downtime, and improve overall efficiency in managing vehicle repairs. | They would like to have a designed website for an inventory and payroll system to manage their products, employee details, and salary. They would also like to conduct a sales analysis of their products to evaluate performance and possible expansion. | Founded in 2020, MotorPH aims to offer private transportation alternatives to the Filipino population. We aspire to become the primary preference for Filipinos seeking cost-effective and competitive motorcycle options.Motor PH is a private company that provides good, effective and affordable vehicle to filipino for over 4 years now. | Their problem is how they can be the first choice for Filipinos looking for competitive and reasonably priced motorcycles.
2 | What are your assumptions about the requirement? | Assumptions about the client's requirements include the expectation that the new payroll system should seamlessly integrate with existing processes, with a dedicated budget for development and implementation. Successful execution relies on stakeholder engagement and cooperation, and compliance with legal and regulatory requirements is essential. It is assumed that the development team has the necessary resources and expertise, and the system must be user-friendly for efficient utilization by the client's staff. | The client wants the new payroll system to integrate seamlessly with existing processes. There is a budget allocated for the development and implementation of the new system. Stakeholder engagement and cooperation are expected for successful implementation. The new system should comply with relevant legal and regulatory requirements. The development team has access to necessary resources and expertise. The system should be user-friendly for efficient utilization by the client's staff. | UI for presenting Employees information and Weekly salary calculations | A user-friendly interface displaying employee details, a system capturing and storing hours worked, calculations based on a predetermined hourly rate for gross salary, generic deductions, and accurate testing. | The requirements are too simple and that is to open branches nationwide so we need to improve our payroll system so that we can release employees' salaries without delay. We also need to improve our overall databases like their product listing, employee details, and other stuff to easily track their transactions. | My assumption could be the requirement in motorPH is related to the automotive industry or motor vehicles which is specifically made only for the Philippines. | They will need a one stop shop website to use for both their employees and prospect customers. | To understand what the client needs and objectives to narrow down as we we go along. | Develop an application that can present employee details and automate the calculation of the weekly salary based on the number of hours worked and deductions.
3 | What is the end goal for completing this? | The project's end goal is to establish the foundation for a payroll and employee management system tailored to MotorPH's evolving requirements. Phases will be introduced over time to accommodate expanding needs. The envisioned outcome is an end-to-end inventory and payroll system that effectively manages products, employee details, and salaries. This system will be developed in carefully planned phases, allowing for gradual expansion of requirements. | The ultimate goal is to bring out an upgraded MotorPH Payroll System that fixes current problems, boosts productivity, and supports the company's primary objective of being the leading option for Filipinos in the motorbike sector. Payroll procedures should be streamlined by this system, guaranteeing accuracy, promptness, and improved customer and employee service. | The project's completion intends to give MotorPH a reliable, automated system that not only satisfies their present requirements but also sets them up for future growth and success | To lay the groundwork for a payroll and employee management system suited to MotorPh's requirements. They will be expanding the requirements per phase as the months progress. | Our end goal is to have an end-to-end inventory and payroll system to manage our products, employee details, and salary. We're hoping to get this system built in phases. We will be expanding the requirements per phase as the months progress. | The end goal for this program is to let the individuals to contribute to the advancement of motor practice and to have a simple solution that would help us manage our inventory. | Their end goal is to have an end-to-end inventory and payroll system to manage their products, employee details, and salary. | To provide the goals and objectives mappped out for MOTOR PH in an effective manner. | Their main goal is to manage they products, employee information, and salary through an end-to-end inventory and payroll system. They intend to build this system carefully and will be expanding the requirements for each phase.
4 | What features are the client looking for? | Specific features the client is looking for in the payroll system include: Employee Details Presentation Hours Worked Calculation Gross Wage Calculation Net Wage Calculation The client wants the system to compute hours worked, calculate gross weekly income based on those hours, and determine the net weekly salary after applying general deductions. For MotorPH's end-to-end inventory and payroll system, the desired features include presenting employee information in a prescribed format (employee number, name, birthday), calculating weekly hours worked, computing gross weekly salary based on hours worked, and determining net weekly salary after applying generic deductions. Additionally, the client is specifically looking for advanced safety features and good performance in the MotorPH system. The system should cover inventory data, payroll management, employee databases, and sales and product analysis. | The client needs precise documentation in the form of RAD and SDD and is looking for a full solution for their payroll system. They anticipate receiving a clearly defined business technology proposal that outlines the characteristics and goals of the suggested solution. A functional requirements document that outlines the requirements of the payroll system and a comprehensive database design that incorporates data models, normalization, schema design, indexing, and data integrity are also desired by the customer. The end objective is a precise blueprint that directs the creation, application, and upkeep of the MotorPH Payroll System and is provided in the Database Design Document. | Employee Details Presentation Hours Worked Calculation Gross Wage Calculation Net Wage Calculation | The client is searching for a system that can compute the number of hours worked by an employee in a given week, calculate the gross weekly income based on those hours worked, and determine the net weekly salary following the application of general deductions. | The MotorPh is looking for these features: End-to-end inventory and payroll system to manage the company's products, employee details, and salary. This how the features should look like: presents employee information in the prescribed format (employee number, employee name, birthday). calculates the number of hours an employee has worked in a week. calculates the gross weekly salary of an employee based on hours worked. calculates the net weekly salary of an employee after applying generic deductions. | The client is specifically looking for motorPH to have advanced safety features and a good performance. | Inventory data, payroll system, employee database, and sales & products analysis. | Basic presentation of employee details and automatic salary calculation (through code) based on the number of hours worked and basic deductions.(End-to-end inventory, payroll system). | The client expects to see a working code that fulfills these requirements within 11 weeks, with each phase completed according to the stated timeline.
5 | Are the features part of a process? Is yes, what are the steps? | The Steps provided by the client for the payroll system's features are: Presentation of employee details. Calculation of hours worked. Calculation of gross weekly salary. Application of generic deductions to calculate net weekly salary. For the specific timeline-based process, the steps outlined include: Visualize and present the application in Week 1. Design a simple code in Weeks 2-3. Visualize requirements in Week 4. Employee details presentation in Week 5. Hours worked calculation in Week 6. Gross wage calculation in Week 7. Net wage calculation in Week 8. Testing and revision in Weeks 9-10. Submission of the final output in Week 11. | The process involves first analyzing and documenting the current system's gaps and issues in the Requirements Analysis Document (RAD). Then, the System Design Document (SDD) is developed, accompanied by a Business Technology Proposal. Functional requirements are detailed in the Functional Requirements Document (FRD), leading to the design of the database structure. The final step includes comprehensive documentation through the Database Design Document (DBDD), serving as a blueprint for the development, implementation, and maintenance of the new MotorPH Payroll System. | Yes, features are often integral parts of a process. Features can refer to specific functionalities, characteristics, or attributes of a product, system, or service. 1. Identifying Requirements 2. Prioritizing Features 3. Designing Features 4. Development and Implementation 5. Testing and Validation 6. Feedback and Iteration 7. Debugging 8. Monitoring and Maintenance | Yes and these steps are: - Presentation of employee details. - Calculation of hours worked. - Calculation of gross weekly salary. - Application of generic deductions to calculate net weekly salary. | Yes, the features stated above are part of the process. Here is the step-by-step process: Week 1: Visualize and present what the application will look like. Week 2-3: Design a simple code. Week 4: Visualization of our requirements Week 5: Employee details presentation Week 6: Hours worked calculation Week 7: Gross wage calculation Week 8: Net wage calculation Week 9-10: Testing and revision Week 11: Submission of final output | Yes, for me the steps are typically include conducting through risk assessments, implementing appropriate safety measures, providing training to personnel, analyzing data to identify areas of improvement, and continuously analyzing the lessons that they learned. | Yes, there were indicated phases in the website. | Yes. There is a course plan for tasks needed althrough out the sem succ=h as Phase 1 and 2, that consists of timeline/s and expectations | The steps are: 1: Visualize and present the application 2: Present employee information 3: Calculate hours worked 4: Calculate gross weekly salary 5: Calculate net weekly salary 6: Testing and revision 7: Submission of final output
6 | Do you have thoughts on how this feature can be developed differently? | Several strategies for developing this feature could enhance the overall efficacy and adaptability of the MotorPH Payroll System: Agile Development for Ongoing Modifications User-Centric Design Modular Structure for Adaptability Cloud-Based Solution for Scalability Automation and AI Integration For data security considerations: Confidentiality Measures Security Assessments Access Control Encryption While the approach to development may evolve during the project, having a solid execution plan is crucial. Regular communication with the client is recommended to ensure alignment and the successful delivery of the MotorPH Payroll System. As the project progresses, practical solutions and optimizations can be identified for a smoother development process. | Several strategies for creating this feature could include using agile development for ongoing modifications, putting user experience first with user-centric design, putting in place a modular structure for adaptability, taking into account a cloud-based solution for scalability, and combining automation and AI to increase productivity. Every option seeks to increase the system's overall efficacy and adaptability in order to better satisfy MotorPH's payroll requirements. | One alternative approach to feature development could involve employing rapid prototyping techniques to quickly iterate and gather feedback on various feature concepts before committing to a detailed design and implementation plan. Additionally, adopting a more collaborative and cross-functional approach of the involve parties, could lead to more innovative and holistic solutions. | Put safety measures in place to safeguard confidential employee data, particularly if the system is managing financial and personal information. This may consist of frequent security assessments, limited access, and encryption. | No, but I am sure while working on this project I can figure out the best way to develop it the easy way, What more important is that we have a solid plan how to execute this project and along the ways can come up the best solution to finish it successfully. | None | None | For now, the idea is still foggy since I am just starting to deep dive on this field for Motor PH. | It is important to note that this is a high-level overview, and the actual implementation may require additional details and considerations. Regular communication with the client throughout the development process is recommended to ensure alignment and successful delivery of the project.
7 | How will you know that the requirements have been completed? | Confirmation after Weeks 9-10 Testing and Revision: Testing Success Working Demo or Prototype User Acceptance Testing (UAT) Quality Assurance Usability or Performance Testing Feedback and Iteration Client Testing and Approval Achievement of Goals/Objectives Each of these measures contributes to a comprehensive assessment of requirements completion for the MotorPH Payroll System. Regular communication and collaboration with stakeholders throughout the process can further enhance the verification process. | Confirmation of requirements completion can be obtained by document approval, testing success, input from stakeholders, and alignment with MotorPH's business objectives. Furthermore, a working demo or prototype can provide verifiable proof that the requirements have been fulfilled. | Review and Approval, User Acceptance Testing, Quality Assurance, Usability or Performance Testing, Feedback and Iteration | They will be considered completed when the system consistently and accurately provides employee details, calculates hours worked, and computes gross and net compensation, with successful testing and any necessary adjustments made. | I will know if the requirements have successfully after weeks 9-10 which is testing and revision and if the system runs successfully without encountering any problems. | When all requirements are met and successful. | After client gets to test and check the website to confirm everything's completed. | When the goals/objectives have been accomplished and evidently provides what the client needs from the start. | After running some test and revised potential error.
8 | Where does the process start? What happens next? | For the week-based approach: Week 1-2: The process begins in Week 1 with visualizing and presenting the application. By Week 2, the focus shifts to designing the code for inputting payroll system, employee details, and salaries. | Analyzing and identifying problems with the current payroll system is the first step in the process. The group then produces various documents, including a business technology proposal, a requirements analysis document, and a system design document. The Database Design Document represents the culmination of the team's thorough documentation, which began with the specification of functional requirements and database design. They then go on and use the blueprint as a guide to create, install, and maintain the new MotorPH Payroll System. | Initial Planning, Requirements Analysis and Documentation. Next is interface design. | It starts from week 4 when the process begins with comprehending the visualization needs. Next, development starts in Week 5 with the presentation of employee details. Then, in the following weeks, the hours worked, gross wage, and net wage calculations are progressively implemented. | The process starts at week 1 where we visualize and present what the application will look like followed by designing the code that will use to input the payroll system, employees' details and salaries. | Base on my understanding it starts with the initial assessment of the vehicle's condition and the identification of electrical issues. After the initial assessment, they proceed to detailed inspection of the vehicle's components, followed by the maintenance tasks to ensure good performance and functionality. | Process starts in planning, visualizing how the needs will be met step-by-step. | It starts from week 2 until the end of this semester. | Process begins with a mission objective and end with achievements of the business objective of providing a result that provides customer value.
9 | Where will the results be displayed? | Website: A website project, the results may be prominently displayed on the website, including relevant pages and sections. | Usually, the outcomes will be shown and kept in a safe online database that is available to pertinent parties involved in the creation and execution of the MotorPH Payroll System. Team members and decision-makers may be able to access and examine the material on a dedicated platform, shared drive, or project management application. | Through demonstration of the UI or presenting the features. | Depending on MotorPH's needs, the results will likely be shown on a user interface. | The result will be displayed during the submission of outputs which is in Week 11. | The results will be displayed on the website's homepage or it will be shown in the "Search Results" section. | Website |  | Database
10 | What details or information do you need to know so you can initiate the task? | I need information on the current system, stakeholder requirements, budget, timing, technical infrastructure, legal issues, and user input before I can begin improving the MotorPH payroll system. With this knowledge, a solution that specifically addresses the needs and objectives of MotorPH may be developed. | I need information on the current system, stakeholder requirements, budget, timing, technical infrastructure, legal issues, and user input before I can begin improving the MotorPH payroll system. With this knowledge, a solution that specifically addresses the needs and objectives of MotorPH may be developed. | Requirements, Timeline, Employees Data, Company Policies, Budget | There needs to be more specific details about the desired format for the employee details presentation, the method of input for hours worked, and any other unique requirements MotorPH may have must be provided. | I need proper skills to navigate the programming language that I am going to use in this project. | You need the details or Information of motor vehicle, the make and model of the vehicle, the vehicle identification number, the current location of the vehicle, the specific task or service required, any relevant symptoms or issues with the vehicle, the desired date and time for the task, and any additional instructions or requirements related to the task. | The tool to be used and probably guidance on how to start. | Implementation Simulation Troubleshooting and Risk Reduction Documentation: Document the network design, including configuration, network diagrams, troubleshooting steps, and risk reduction security policies. To design and test the implementation (through Packet Tracer) of a reliable network design and IP scheme for MotorPH's headquarters that meets the company's current and future business needs. The design should accommodate an estimated HR personnel growth of 30% in the near future. | Everything about their business plan
11 | Are there alternative scenarios that you can think of? | Other possibilities include contracting out the development, putting a staged strategy in place, looking into cloud-based solutions, integrating with current systems, or putting user training initiatives in place. The decision is based on the unique requirements and limitations of MotorPH. | Other possibilities include contracting out the development, putting a staged strategy in place, looking into cloud-based solutions, integrating with current systems, or putting user training initiatives in place. The decision is based on the unique requirements and limitations of MotorPH. |  | Yes, there are scenarios like working overtime because if workers put in more hours than the typical workday, they may be entitled to overtime pay at a different rate. | As of now, NONE. Still navigating and learning the required skills and knowledge. | None for now. | None | None as of now. | None
12 | What are the tasks that need to be tracked? | Tasks to track include gathering requirements, creating system design documents, finalizing functional requirements, designing the database, comprehensive documentation, development and implementation stages, user training, budget adherence, timeline, and ensuring legal compliance. Monitoring these tasks ensures a successful refinement of the MotorPH payroll system. | Tasks to track include gathering requirements, creating system design documents, finalizing functional requirements, designing the database, comprehensive documentation, development and implementation stages, user training, budget adherence, timeline, and ensuring legal compliance. Monitoring these tasks ensures a successful refinement of the MotorPH payroll system. | Timeline, Plan | Monitoring task progress involves keeping updated on design and visualization developments, executing employee detail presentations successfully, calculating hours worked accurately, executing gross and net wage computations correctly, and evaluating test results and necessary adjustments. | The tasks that need to be tracked are end-to-end inventory and payroll system to manage our products, employee details, and salary | Addressing maintenance issues, ensuring efficient fuel usage, optimizing driver schedules and routes, managing inventory effectively, and monitoring fleet performance. | Everything. From planning to the status of each step to executioning, testing. | Product Inventory Report: a descriptive overview and analysis of the products offered by our business. Analytical Dashboard: a visual overview that showcases our offered products and trends in sales performance within the given period. Business Analysis Report: a written report that provides a descriptive overview of the business’ objectives and offered products, insights on sales performance, and a summary of findings and projections. | Tracking potential risk or error
13 | Do the features indicated by the client meet their current need or solve the problem they're trying to solve? | Yes, the features outlined by the client, including detailed documentation, system design, and database design, are intended to address the identified issues in the current payroll system, meeting their current needs and resolving existing problems. | Yes, the features outlined by the client, including detailed documentation, system design, and database design, are intended to address the identified issues in the current payroll system, meeting their current needs and resolving existing problems. | Yes, Phase 1 looks to be aligned with MotorPH's actual needs, especially with regard to payroll processing and management of employees. | Yes, the client's proposed features satisfy their current demand to streamline payroll computations and staff detail management. They intend to use it as a first step toward their main goal of growing their company in the future. | I cannot answer that for now but I am sure that I can give a definite answer in the next few weeks of navigating, learning and executing the project. | Yes, the features indicated by the motorph effectively meet their current needs and successfully solve the problem they aim to address. | Yes | As of now the current data is sufficient and will need to reach out to client if the need for additional features arises. | As of now client meet their current needs

## Estimate
Only access and fill out this sheet when instructed to in your learner guide.
Name |  | Group 7
Client Name |  | MotorPH
GUIDE QUESTION | TASK # | RESPONSE
What are the main tasks you need to do? (Insert additional rows if you have more than 10 tasks) | Collect detailed project specifications and user expectations.
Create a comprehensive document outlining system architecture.
Implement the MotorPH payroll system according to specifications.
Design and implement the database structure.
Develop a user-friendly interface for the payroll system.
Conduct thorough testing to ensure system functionality.
Prepare comprehensive user and technical documentation.
Implement robust security measures for data protection.
Conduct training sessions for MotorPH employees.
Deploy the system and monitor ongoing performance.
What do you need to know to accomplish these tasks? (Insert additional rows if you have more than 10 tasks) | Detailed specifications and expectations for the MotorPH project, including features, functionalities, and user requirements.
Understanding of the overall system architecture, including the components, interactions, and data flow within the MotorPH payroll system.
Specific requirements for developing the MotorPH payroll system, including functionalities such as employee information presentation, salary calculations, and deductions.
Information about the structure and data requirements for the MotorPH payroll system database, including employee details and payroll records.
Design preferences and user interface requirements for MotorPH employees, ensuring a seamless and user-friendly experience.
Criteria and scenarios for testing the payroll system to ensure functionality, accuracy, and reliability.
Standards and guidelines for preparing user manuals, system architecture documents, and technical documentation.
Security policies, standards, and specific requirements for safeguarding sensitive employee information and financial data.
Information about the skill levels and training needs of MotorPH employees to tailor training sessions accordingly.
Technical specifications and requirements for deploying the system to the MotorPH environment, including server configurations and network settings.
What additional help do you think you need to be able to do each task? (Insert additional rows if you have more than 10 tasks) | Collaborate with MotorPH stakeholders and subject matter experts to ensure comprehensive understanding of project needs.
Engage with system architects or experienced designers to ensure the proposed architecture aligns with best practices.
Work closely with skilled developers or a development team to efficiently implement the payroll system.
Consult with a database administrator or expert for optimal database design and performance.
Collaborate with UX/UI designers to create an intuitive and visually appealing interface.
Involve dedicated quality assurance professionals to conduct thorough testing and identify potential issues.
Seek assistance from technical writers for clear and comprehensive documentation.
Consult with cybersecurity experts to ensure robust security measures are implemented.
Enlist training specialists or experienced trainers to conduct effective training sessions for MotorPH employees.
Engage with IT specialists for successful deployment, and involve system administrators for ongoing monitoring and maintenance.
Given the nature of the task, the knowledge you need, and any additional help you need, how long do you think it would it take you (in hours) to finish each task? (Insert additional rows if you have more than 10 tasks) | Requirements Gathering: Estimated Time: 30-40 hours Weeks Allocated: 4 weeks Total Hours: 40 hours
System Design: Estimated Time: 40-50 hours Weeks Allocated: 5 weeks Total Hours: 50 hours
Payroll System Development: Estimated Time: 80-100 hours Weeks Allocated: 8 weeks Total Hours: 80 hours
Database Design: Estimated Time: 30-40 hours Weeks Allocated: 4 weeks Total Hours: 40 hours
User Interface Design: Estimated Time: 40-50 hours Weeks Allocated: 5 weeks Total Hours: 50 hours
Testing and QA: Estimated Time: 50-60 hours Weeks Allocated: 6 weeks Total Hours: 60 hours
Documentation: Estimated Time: 20-30 hours Weeks Allocated: 3 weeks Total Hours: 30 hours
Security Implementation: Estimated Time: 40-50 hours Weeks Allocated: 5 weeks Total Hours: 50 hours
Training Sessions: Estimated Time: 20-30 hours Weeks Allocated: 3 weeks Total Hours: 30 hours
Deployment and Monitoring: Estimated Time: 30-40 hours Weeks Allocated: 4 weeks Total Hours: 40 hours
In this course, you are expected to dedicate 7.5 hours per week. Based on the total number of hours you estimated, how many weeks will you need to finish your outputs? | These hour estimates are adjusted to fit the 10-hour-per-week commitment over the 8-week period (from Week 4 to Week 12, allowing for a balanced distribution of tasks within the given constraints.

## Project Plan
Only access and fill out this sheet when instructed to in your learner guide. Use the template below or use any free project management tool available online.
INSTRUCTIONS
Use the guide below to help you fill out this template. TASK # - Use whole numbers to specify main tasks (e.g., 1,2,3). If the task is considered a sub-task, advance the numbering using decimal points to still identify what the main task is (e.g., 1.1, 1.2, 1.3). TASK - Describe the task. Start tasks with verbs/action words to add specificity, e.g., List requirements instead of simply Requirements. DEPENDENCY - Identify the task which cannot be started unless a previous task has been completed. Leave this blank if there is no dependency. OWNER - Identify the person responsible for completing the task. START DATE & END DATE - Identify the planned start and end dates per task. The main task's start and end-date should be the start date of the first sub-task and the end date of the last sub-task. The last end date in your project plan should be within the submission dates indicated in your syllabus. STATUS - By default, all tasks start with a Not Started status. Change the status to In Progress if it's already being worked on and Completed once the task is done. ACTUAL START & END DATE - Specify the actual start and end dates per task. This allows you to identify whether you were able to adhere to your initial timelines and if you will be able to complete the rest of your tasks on time. If you see that you don't have sufficient time, you need to work with your team to decide on alternatives or adjustments. NOTES - Indicate any notes or reminders you may have for each task.
TASK # | TASK | DEPENDENCY | OWNER | START DATE | END DATE | STATUS | ACTUAL START DATE | ACTUAL END DATE | NOTES
1 | Requirements Gathering |  | 6 | - | - | Completed | - | - | Already finished before grouping due to individual activities
1.1 | Define project scope and objectives |  | 3 | - | - | Completed | - | - | Already finished before grouping due to individual activities
1.2 | Identify stakeholders and gather requirements | 1.1 | 2 | - | - | Completed | - | - | Already finished before grouping due to individual activities
1.3 | Conduct user interviews and surveys | 1.2 | 5 | - | - | Completed | - | - | Already finished before grouping due to individual activities
1.4 | Analyze existing documentation and data | 1.3 | 8 | - | - | Completed | - | - | Already finished before grouping due to individual activities
2 | System Design |  | 1 | 2024-02-05 | 2024-02-05 | Completed | 2024-02-03 | 2024-02-04 | Already finished before the proposed end date
2.1 | Develop a comprehensive system architecture |  | 6 | 2024-02-05 | 2024-02-06 | Completed | 2024-02-03 | 2024-02-05 | Already finished before the proposed end date
2.2 | Design system components and interactions | 2.1 | 6 | 2024-02-05 | 2024-02-07 | Completed | 2024-02-05 | 2024-02-06 | Already finished before the proposed end date
2.3 | Create data flow diagrams and system models | 2.2 | 1 | 2024-02-05 | 2024-02-08 | Completed | 2024-02-05 | 2024-02-06 | Already finished before the proposed end date
2.4 | Document system design | 2.3 | 2 | 2024-02-05 | 2024-02-09 | Completed | 2024-02-05 | 2024-02-08 | Already finished before the proposed end date
3 | Payroll System Development |  | 8 | 2024-02-12 | 2024-02-12 | Completed | 2024-02-10 | 2024-02-11 | Already finished before the proposed end date
3.1 | Set up development environment |  | 4 | 2024-02-12 | 2024-02-13 | Completed | 2024-02-10 | 2024-02-11 | Already finished before the proposed end date
3.2 | Implement employee details presentation |  | 3 | 2024-02-12 | 2024-02-14 | Completed | 2024-02-11 | 2024-02-13 | Already finished before the proposed end date
3.3 | Code hours worked calculation | 3.2 | 4 | 2024-02-12 | 2024-02-15 | Completed | 2024-02-11 | 2024-02-14 | Already finished before the proposed end date
3.4 | Code gross weekly salary calculation | 3.3 | 3 | 2024-02-12 | 2024-02-16 | Completed | 2024-02-11 | 2024-02-16 | Already finished before the proposed end date
3.5 | Code net weekly salary calculation | 3.4 | 6 | 2024-02-12 | 2024-02-17 | Completed | 2024-02-11 | 2024-02-17 | Already finished before the proposed end date
4 | Database Design |  | 2 | 2024-02-19 | 2024-02-19 | Completed | 2024-02-16 | 2024-02-18 | Already finished before the proposed end date
4.1 | Define database requirements |  | 4 | 2024-02-19 | 2024-02-20 | Completed | 2024-02-16 | 2024-02-18 | Already finished before the proposed end date
4.2 | Create database structure | 4.1 | 4 | 2024-02-19 | 2024-02-21 | Completed | 2024-02-17 | 2024-02-18 | Already finished before the proposed end date
4.3 | Implement data models and normalization | 4.2 | 5 | 2024-02-19 | 2024-02-22 | Completed | 2024-02-17 | 2024-02-19 | Already finished before the proposed end date
4.4 | Design schema and indexing | 4.3 | 5 | 2024-02-19 | 2024-02-23 | Completed | 2024-02-17 | 2024-02-19 | Already finished before the proposed end date
4.5 | Ensure data integrity | 4.4 | 5 | 2024-02-19 | 2024-02-24 | Completed | 2024-02-17 | 2024-02-19 | Already finished before the proposed end date
5 | User Interface Design |  | 4 | 2024-02-26 | 2024-02-26 | Completed | 2024-02-26 | 2024-02-26 | Already finished before the proposed end date
5.1 | Gather user interface requirements |  | 3 | 2024-02-26 | 2024-02-27 | Completed | 2024-02-26 | 2024-02-27 | Already finished before the proposed end date
5.2 | Develop wireframes and prototypes |  | 3 | 2024-02-26 | 2024-02-28 | Completed | 2024-02-26 | 2024-02-08 | Already finished before the proposed end date
5.3 | Design the user interface | 5.2 | 4 | 2024-02-26 | 2024-02-29 | Completed | 2024-02-26 | 2024-02-28 | Already finished before the proposed end date
5.4 | Review and refine UI design | 5.3 | 5 | 2024-02-26 | 2024-03-01 | Completed | 2024-02-27 | 2024-03-01 | Already finished before the proposed end date
6 | Testing and QA |  | 1 | 2024-03-04 | 2024-03-04 | Completed | 2024-03-02 | 2024-03-05 | Already finished before the proposed end date
6.1 | Develop test cases and scenarios |  | 2 | 2024-03-04 | 2024-03-04 | Completed | 2024-03-02 | 2024-03-05 | Already finished before the proposed end date
6.2 | Conduct unit testing | 3.5 | 2 | 2024-03-04 | 2024-03-05 | Completed | 2024-03-02 | 2024-03-05 | Already finished before the proposed end date
6.3 | Perform system testing | 4.5 | 2 | 2024-03-04 | 2024-03-05 | Completed | 2024-03-04 | 2024-03-06 | Already finished before the proposed end date
6.4 | Address and fix identified issues | 6.3 | 7 | 2024-03-04 | 2024-03-06 | Completed | 2024-03-04 | 2024-03-06 | Already finished before the proposed end date
6.5 | Conduct user acceptance testing | 5.4 | 2 | 2024-03-04 | 2024-03-06 | Completed | 2024-03-04 | 2024-03-06 | Already finished before the proposed end date
7 | Deployment and Monitoring |  | 8 | 2024-03-11 | 2024-03-17 | Completed | 2024-03-09 | 2024-03-14 | Already finished before the proposed end date
7.1 | Plan system deployment |  | 5 | 2024-03-11 | 2024-03-20 | Completed | 2024-03-09 | 2024-03-17 | Already finished before the proposed end date
7.2 | Deploy the system | 6.5 | 2 | 2024-03-11 | 2024-03-20 | Completed | 2024-03-09 | 2024-03-17 | Already finished before the proposed end date
7.3 | Monitor system performance | 7.2 | 7 | 2024-03-11 | 2024-03-20 | Completed | 2024-03-10 | 2024-03-19 | Already finished before the proposed end date